## Before you start
Chedam manual tests: P5 Connect and enrich (grows with each build step; tested in the next test week)
Laptop and iPhone; Android later. Linked card tests need a Square sandbox account and access token (or a Square Terminal).
Sample people: Demo Owner, Mira Manager, Ana Accountant, Cal Cashier, Sam Staff.
For each row: do what it says, compare with 'What should happen', choose Pass / Fail / Blocked, and write what happened when it is not a Pass.

## Tests
ID | Area | Device / needs | What to do | What should happen | Result | Notes (what happened) | Tester | Date
C01 | Card processor | Laptop (owner) | Home → Card processor; paste a wrong token, Connect | Refused: Square says the token is not valid | Not tested
C02 | Card processor | Laptop (owner) | Paste the Square sandbox access token (Sandbox), Connect | Connected: the account name, the main location chosen; the token is not shown again | Not tested
C03 | Card processor | Laptop (manager) | Look for Card processor on Home | No tile (owner only) | Not tested
C04 | Card processor | Laptop (owner) | Pair a terminal: name 'Front terminal', till = the iPhone till; Get a code | A 6-character code and how to type it on the terminal | Not tested
C05 | Card processor | Square Terminal (or the sandbox device) | Sign in → Use a device code → type it | Within seconds the screen says Paired | Not tested
C06 | Card processor | Laptop (owner) | Link the terminal to another till | Saved; the first till no longer has a terminal | Not tested
C07 | Card processor | Laptop (owner) | Settings → Export data; Activity log for the processor | No token anywhere | Not tested
C08 | Card processor | Laptop (owner) | Disconnect | Card on every till goes back to keying in the amount | Not tested

## Summary
Area | Checks | Pass | Fail | Blocked | Not tested
Card processor
All